## User stories
| Main User Story | Sub-Task
1 | Programs | Add Programs
Update Programs
Delete Programs
Show Program By Id
Show All Programs
2 | Scheduled Programs | Add Scheduled Programs
Update Scheduled Programs
Delete Scheduled Programs
Show All Scheduled Programs
Show Scheduled Program By Id
3 | Applications | Add Application
Update Application
Delete Application
Show Application By Id
Show All Application
4 | Participants | Add Participants
Update Participants
Delete Participants
Show Participant By Id
Show All Participants
Show By Roll Number
5 | Authentication | Login
Logout
Find By Username
6 | Consumer | Admin
Mac
Applicant

## Shailesh
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day
1 | Programs and Scheduled Programs
1.1 | Add Programs and Scheduled Programs
1.1.1 | Service | 3 | 3 | Saturday
1.1.2 | Validations + Exception Handling | 1 | 1 | Monday
1.1.3 | Testing | 1.5 | 1.5 | Tuesday
1.2 | Delete Programs and Scheduled Programs
1.2.1 | Service | 1 | 1 | Saturday
1.2.2 | Validations + Exception Handling | 1 | 1 | Monday
1.2.3 | Testing | 1.5 | 1.5 | Tuesday
1.3 | Update Programs and Scheduled Programs
1.3.1 | Service | 2 | 2 | Saturday
1.3.2 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.3.3 | Testing | 1.5 | 1.5 | Tuesday
1.4 | Show All Programs and Scheduled Programs
1.4.1 | Service | 1 | 1 | Saturday
1.4.2 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.4.3 | Testing | 1 | 1 | Tuesday
1.5 | Show Programs and Scheduled Programs By Id
1.5.1 | Service | 1 | 1 | Saturday
1.5.2 | Validations + Exception Handling | 1 | 1 | Monday
1.5.3 | Testing | 1.5 | 1.5 | Tuesday
1.6 | Consumer-Admin Service
1.6.1 | Service | 1 | 1 | Monday
1.6.2 | Testing | 1.5 | 1.5 | Tuesday

## Siddharth
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day
1 | Applications
1.1 | Add Applications
1.1.1 | Service | 3 | 3 | Saturday
1.1.2 | Validations + Exception Handling | 1 | 1 | Monday
1.1.3 | Testing | 1.5 | 1.5 | Tuesday
1.2 | Delete Applications
1.2.1 | Service | 1 | 1 | Saturday
1.2.2 | Validations + Exception Handling | 1 | 1 | Monday
1.2.3 | Testing | 1.5 | 1.5 | Tuesday
1.3 | Update Applications
1.3.1 | Service | 2 | 2 | Saturday
1.3.2 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.3.3 | Testing | 1.5 | 1.5 | Tuesday
1.4 | Show All Applications
1.4.1 | Service | 1 | 1 | Saturday
1.4.2 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.4.3 | Testing | 1 | 1 | Tuesday
1.5 | Show Applications By Id
1.5.1 | Service | 1 | 1 | Saturday
1.5.2 | Validations + Exception Handling | 1 | 1 | Monday
1.5.3 | Testing | 1.5 | 1.5 | Tuesday
1.6 | Consumer-Applicant Service
1.6.1 | Service | 1 | 1 | Monday
1.6.2 | Testing | 1.5 | 1.5 | Tuesday

## Sonu
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day
1 | Participants
1.1 | Add Participants
1.1.1 | Service | 3 | 3 | Saturday
1.1.2 | Validations + Exception Handling | 1 | 1 | Monday
1.1.3 | Testing | 1.5 | 1.5 | Tuesday
1.2 | Delete Participants
1.2.1 | Service | 1 | 1 | Saturday
1.2.2 | Validations + Exception Handling | 1 | 1 | Monday
1.2.3 | Testing | 1.5 | 1.5 | Tuesday
1.3 | Update Participants
1.3.1 | Service | 1 | 1 | Saturday
1.3.2 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.3.3 | Testing | 1.5 | 1.5 | Tuesday
1.4 | Show All Participants
1.4.1 | Service | 1 | 1 | Saturday
1.4.2 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.4.3 | Testing | 1 | 1 | Tuesday
1.5 | Show Participants By Id
1.5.1 | Service | 1 | 1 | Saturday
1.5.2 | Validations + Exception Handling | 1 | 1 | Monday
1.5.3 | Testing | 1.5 | 1.5 | Tuesday
1.6 | Show Participants By Roll Number
1.6.1 | Service | 1 | 1 | Saturday
1.6.2 | Validations + Exception Handling | 1 | 1 | Monday
1.6.3 | Testing | 1.5 | 1.5 | Tuesday
1.6 | Mac-Consumer Service
1.6.1 | Service | 1 | 1 | Monday
1.6.2 | Testing | 1.5 | 1.5 | Tuesday

## Manish
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day
1 | Authentication
1.1 | Login &Application
1.1.1 | Service | 3 | 3 | Saturday
1.1.2 | Validations + Exception Handling | 1 | 2 | Monday
1.1.3 | Testing | 1.5 | 1.5 | Tuesday
1.2 | Logout & Application
1.2.1 | Service | 3 | 3 | Saturday
1.2.2 | Validations + Exception Handling | 1 | 2 | Monday
1.2.3 | Testing | 3 | 3 | Tuesday
1.3 | Find By Username
1.3.1 | Service | 1 | 1 | Saturday
1.3.2 | Validations + Exception Handling | 1 | 2 | Monday
1.3.3 | Testing | 1.5 | 1.5 | Tuesday
1.6 | Consumer-Applicant Service
1.6.1 | Service | 1 | 1 | Monday
1.6.2 | Testing | 1.5 | 1.5 | Tuesday